## About (hidden)
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Green (hidden)
Project: Green
Contoso, Ltd.
Riku Nakano
Project start date: | 2023-10-23 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | November | [27 empty] | December
 | time axis 2023-11-05 to 2023-12-30
Milestone description | Assigned to | Progress | Start | Days | time axis 2023-11-05 to 2023-12-30
Project development
Project charter |  | 25% | 2023-10-26 | 3
Research |  |  | 2023-10-31 | 1
Projections |  | 50% | 2023-10-23 | 10
Stakeholders |  |  | 2023-11-15 | 1 | bar: 2023-11-15
Review |  | 10% | 2023-11-01 | 6
Contracts
Proposals |  | 60% | 2023-11-01 | 13
Document review |  | 50% | 2023-11-02 | 9
Bid date |  | 33% | 2023-11-10 | 11
Award date |  |  | 2023-11-19 | 1 | bar: 2023-11-19
Finalize |  |  | 2023-11-20 | 24
Design
Feasibility study |  |  | 2023-11-10 | 4
Submit permit applications |  |  | 2023-11-14 | 14
Design proposal |  |  | 2023-11-30 | 6
Materials |  |  | 2023-12-13 | 3
Equipment |  |  | 2023-12-05 | 19
Testing
Environment |  |  | 2023-12-02 | 15
System test |  |  | 2023-11-24 | 5
Issues/bugs |  |  | 2024-01-14 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Blue (hidden)
Project: Blue
Contoso, Ltd.
Gurpreet Bawa
Project start date: | 2023-10-23 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | November | [27 empty] | December
 | time axis 2023-11-05 to 2023-12-30
Milestone description | Assigned to | Progress | Start | Days | time axis 2023-11-05 to 2023-12-30
Title 1
Task 1 |  | 25% | 2023-10-26 | 3
Task 2 |  |  | 2023-10-31 | 1
Task 3 |  | 50% | 2023-10-23 | 10
Task 4 |  |  | 2023-11-15 | 1 | bar: 2023-11-15
Task 5 |  | 10% | 2023-11-01 | 6
Title 2
Task 1 |  | 60% | 2023-11-01 | 13
Task 2 |  | 50% | 2023-11-02 | 9
Task 3 |  | 33% | 2023-11-10 | 11
Task 4 |  |  | 2023-11-19 | 1 | bar: 2023-11-19
Task 5 |  |  | 2023-11-20 | 24
Title 3
Task 1 |  |  | 2023-11-10 | 4
Task 2 |  |  | 2023-11-14 | 14
Task 3 |  |  | 2023-11-30 | 6
Task 4 |  |  | 2023-12-13 | 3
Task 5 |  |  | 2023-12-05 | 19
Title 4
Task 1 |  |  | 2023-12-02 | 15
Task 2 |  |  | 2023-11-24 | 5
Task 3 |  |  | 2024-01-14 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## pROJEXT X
Project X: Walkway Casino
Project X
| Project start date: | 2023-01-28
 | time axis 2023-01-28 to 2023-03-24
| Project | Assigned to | Progress | Start | End | Days | time axis 2023-01-28 to 2023-03-24
0
Site Work
| raising server room floor | RackSolutions | 25% | 2023-01-28 | 2023-02-01 | 4 | bar: 2023-01-28 to 2023-02-01
0 | installing fire prevention systems | Fire Department8 | 40% | 2023-01-28 | 2023-02-01 | 4 | bar: 2023-01-28 to 2023-02-01
| installing air conditions | Escape Cooling | 50% | 2023-01-28 | 2023-01-31 | 3 | bar: 2023-01-28 to 2023-01-31
| Installing CCTV footage | Atlas Security | 25% | 2023-01-30 | 2023-02-03 | 4 | bar: 2023-01-30 to 2023-02-03
Prep Work
| Building switch checks | Project X | 10% | 2023-02-02 | 2023-02-04 | 2 | bar: 2023-02-02 to 2023-02-04
| Create Configs | Project X | 50% | 2023-02-02 | 2023-02-04 | 2 | bar: 2023-02-02 to 2023-02-04
| Cable measurement | Project X | 33% | 2023-02-02 | 2023-02-06 | 4 | bar: 2023-02-02 to 2023-02-06
| Cable labling | Project X | 45% | 2023-02-05 | 2023-02-08 | 3 | bar: 2023-02-05 to 2023-02-08
| Task 5 |  |  | 2023-11-20 | 2023-12-14 | 24
Casino floor and Shops
| Drilling |  |  | 2023-02-05 | 2023-02-05 | 1 | bar: 2023-02-05
| installing conduits for cables and ventilation | Project X | 25% | 2023-02-05 | 2023-02-07 | 2 | bar: 2023-02-05 to 2023-02-07
| cleaning |  |  | 2023-02-05 | 2023-02-05 | 1 | bar: 2023-02-05
| cabling | Project X | 50% | 2023-02-07 | 2023-02-10 | 3 | bar: 2023-02-07 to 2023-02-10
| installing patch panels and switches |  | 80% | 2023-02-07 | 2023-02-11 | 4 | bar: 2023-02-07 to 2023-02-11
| installing access points | RAIN.co | 80% | 2023-02-07 | 2023-02-10 | 3 | bar: 2023-02-07 to 2023-02-10
| instaliing cabinets | Project X | 80% | 2023-02-07 | 2023-02-11 | 4 | bar: 2023-02-07 to 2023-02-11
| Shop equipment and Casino slots/equip | CasinoSupply.co | 60% | 2023-02-07 | 2023-02-14 | 7 | bar: 2023-02-07 to 2023-02-14
| Install radio system | Heytera Radio & Co | 10% | 2023-02-12 | 2023-02-14 | 2 | bar: 2023-02-12 to 2023-02-14
Server Room
| Drilling | Project X | 80% | 2023-02-09 | 2023-02-10 | 1 | bar: 2023-02-09
| Trunking | Project X | 25% | 2023-02-09 | 2023-02-12 | 3 | bar: 2023-02-09 to 2023-02-12
| cleaning |  | 10% | 2023-02-12 | 2023-02-12 | 1 | bar: 2023-02-12
| cabling | Project X | 25% | 2023-02-12 | 2023-02-16 | 4 | bar: 2023-02-12 to 2023-02-16
| installing servers | Project X | 0% | 2023-02-13 | 2023-02-18 | 5 | bar: 2023-02-13 to 2023-02-18
| installing switches | Project X | 0% | 2023-02-13 | 2023-02-17 | 4 | bar: 2023-02-13 to 2023-02-17
| installing firewalls | Project X | 10% | 2023-02-14 | 2023-02-17 | 3 | bar: 2023-02-14 to 2023-02-17
Management Room (IT)
| drilling and trunking | Project X | 0% | 2023-02-14 | 2023-02-16 | 2 | bar: 2023-02-14 to 2023-02-16
| cleaning |  | 25% | 2023-02-14 | 2023-02-14 | 1 | bar: 2023-02-14
| cabling | Project X | 50% | 2023-02-14 | 2023-02-14 | 1 | bar: 2023-02-14
| installing printers and access points | Project X | 0% | 2023-02-16 | 2023-02-20 | 4 | bar: 2023-02-16 to 2023-02-20
Testing
| verifying connectivity | Project X | 0% | 2023-02-20 | 2023-02-20 | 1 | bar: 2023-02-20
| user training | CasinoSupply.co / Project X | 0% | 2023-02-02 | 2023-02-16 | 14 | bar: 2023-02-02 to 2023-02-16
| installing access card machines | Project X | 0% | 2023-02-20 | 2023-02-21 | 1 | bar: 2023-02-20
| Final System Testuing ( User login) | Project X | 0% | 2023-02-28 | 2023-02-28 | 1 | bar: 2023-02-28
To add more data, Insert new rows ABOVE this one | bar: 2023-02-28